## RTM
REQUIREMENNTS TRACEBILITY MATRIX
Project Name: Demo Web Shop – demowebshop.tricentis.com |  |  |  | Document Author: Mohammed Bazzar
Req # Unique ID | Requirements Name / Description | Business Need, Justification | User Story or Work Package | Assigned To | Test Cases | Current Status | Notes
RQ-1 | User Registration | Allow new users to create accounts with validated personal details and login credentials so the platform can maintain a registered user base. | As a new visitor, I want to register an account so I can log in and place orders. | Mohammed Bazzar | TC-Reg-01 to TC-Reg-05 | Complete | TC-Reg-05 Failed – Bug-Register-01
RQ-2 | User Login & Logout | Allow registered users to authenticate securely and log out, protecting account access and session integrity. | As a registered user, I want to log in and out of my account so my session is secure. | Mohammed Bazzar | TC-LOG-01 to TC-LOG-03 | Complete | All Passed
RQ-3 | Product Search | Enable users to search for products by keyword and view matching results so they can find items efficiently. | As a shopper, I want to search products so I can quickly locate what I need. | Mohammed Bazzar | TC-Search-01 to TC-Search-02 | Complete | All Passed
RQ-4 | Cart | Allow users to add products to the cart from multiple entry points (product page, search results, home page) with dynamic total updates. | As a shopper, I want to manage my cart so I can review and adjust my order before checkout. | Mohammed Bazzar | TC-Cart-01 to TC-Cart-03 | Complete | All Passed
RQ-5 | Wishlist | Allow users to save products to a wishlist for future purchase and verify wishlist button availability across products. | As a logged-in user, I want to save products to my wishlist so I can purchase them later. | Mohammed Bazzar | TC-WISH-01 to TC-WISH-03 | Complete | TC-WISH-03 Failed – Bug-Wish-02